**Re: TD04F Situation Report No. 35 as at 0800 Hours – Monday 02 January 2017**

There has been no change to SITREP No.34. The FRA Contractors are working in the interior of Naitasiri today in the attempt to open all roads that are still inaccessible to vehicles.

Below is the latest update of roads closed:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Division** | **Road Name** | **Location** | **Description** | **Date to be resolved** |
| 1 | Central | Nasiriti Rd | RP 6322 | Culvert undermined | Unknown |
| 2 | Central | Wailoa Rd | RP 38000 | Multiple slips | Unknown  |
| 3 | Central | Nabukavesi Rd | RP 3200  | Road drop out. Geotech input required.  | Subject to geotechnical assessments.**Alternative routes available.** |
| 4 | Central | Nadovou Nasali Rd | various |  | Unknown |
| 5 | Central | Laselevu Rd | RP 1046 |  | Unknown |
| 6 | Central | Nakorosule Rd | RP 10900 |  | Unknown |
| 7 | Central | Sawanikula Bukunivatu Rd | RP 2013 |  | Unknown |
| 8 | Central | Nuku Village Rd | RP 300 |  | Unknown |
| 9 | Northern | Rabi Coastal Rd | RP 300 and RP 700 | Two major slips | Mid-January 2017 |
| 10 | Western | Lawaki Nasau Rd | Nawairuku Crossing | Slips and washed out approaches | 05/01/17 |
| 11 | Western | Nubumakita Rd | various | Landslip | 05/01/17 |
| 12 | Eastern | Gau Circular Rd | Navukailagi to Qarani | Land slip | 04/01/17 |

* Kasavu Landslide, located north of the Kasavu/ Baulevu Road Junction on Kings Road is open to light vehicles only and operating as a single lane with potential for full closure if there are further slips. A 5 tonne weight restriction is in place. Allow extra traveling time.
* Gravelling works on the alternative access route is still in progress. The opening of the alternative route will be subject to the results of the geotech investigation. The field investigation has been completed and FRA is waiting for the geotech report.

Below is a link to a map that shows the status of the road network and situation report locations. This is a live link that is updated throughout the day, so do check back regularly to see if road status has changed.

<http://fijiroads.maps.arcgis.com/apps/webappviewer/index.html?id=29ec809564d74baa8cfd6a88e7efd46f>

**Central Division**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Depot | Road Name | Location Description | Status of Damage | Time/Date Reported | Advice to Motorists | FRA Contractors Action that Will be Taken | Expected Road Opening Date | Time/Date Resolved | How Resolved |
| Taunovo | Beqa Rd | Wainikavou Crossing | Appraoch reinstated | 14/12/16 1415 | Open | Monitor water levels | 21/12/2016 1600 hrs | ############# | Approaches backfilled |
| Korovou | Colata Cocoa Rd | Colata Crossing | Underwater | 14/12/16 0800 | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Naqali | Vatulili Rd | Waidradra Crossing | Water receded | 14/12/16 1615 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water Receded |
| Rewa | Dawakoto Rd |   | Flooded | 15/12/16 0600 | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Rewa | Dravuni Rd |   | Water receded | 15/12/16 0600 | Open | Monitor water levels | 16.12.16 |   |   |
| Taunovo | Sadro Rd |   | Flooded | 15/12/16 0730 | Road open | Monitor water levels | 12/16/2016 | 16/12/2016 1551 p.m | Water Receeded |
| Korovou | Naboro Cocoa Rd | Delekado Crossing | Water receded | 15/12/16 0630 | Open | Monitor water levels | 12/15/2016 | 15/12/2016 1400 |   |
| Taunovo | Beqa Rd | Tubarua Crossing | Approach Washout/flooded | 15/12/16 0915 | Road Open | Monitor water levels | 12/20/2016 | 20/12/2016 1401 p.m | Washout approach backfilled. |
| Taunovo | Namosi Rd | Wainikovu Crossing | Flooded | 15/12/16 0915 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1010 a.m | Water Receeded |
| Taunovo | Saliadrau Rd | Wainimakutu Crossing | Flooded | 15/12/16 0915 | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Naqali | Navulokani Rd | Waiwata Crossing | Water receded | 15/12/16 1000 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Naqali | Savu Rd | Savu Bridge 2 | Water receded | 15/12/16 1000 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water Receded |
| Naqali | Navulokani Rd | Waisa Crossing | Water receded | 15/12/16 1000 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Suva Nth | Railagi Rd | Railagi Crossing | Flooded | 15/12/16 1000 | Open to traffic - Caution when crossing  | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Naqali | Lomaivuna Loop Rd | Toda Crossing | Flooded | 15/12/16 1000 | Road Open | Monitor water levels | 12/16/2016 | 16/12/2016 1448 p.m | Water Receeded |
| Naqali | Wailase Rd | Nasi Crossing | Water receded | 15/12/16 1030 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Naqali | Waibau Rd | Waibau bridge | Flooded | 15/12/16 1030 | Closed to all traffic | Monitor water levels | 12/16/2016 | 16/12/2016 0818am | Water Has Receeded |
| Suva Sth | Nasivou St | Qauia Village Rd intersection | Flooded | 15/12/16 1045 | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Taunovo | Waiyanitu Rd |   | Flooded | 15/12/16 1045 | Road is open | Monitor water levels | 12/16/2016 | 16/12/2016 1551 p.m | Water Receeded |
| Taunovo | Waiyanitu Rd | Wainisusu Crossing | Flooded | 15/12/16 1045 | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Taunovo | Tokotoko Rd |   | Flooded | 15/12/16 1045 | Open | Monitor water levels | 12/16/2016 | 16/12/2016 17:13 p.m | Water Receeded |
| Taunovo | Naitonitoni Rd |   | Flooded | 15/12/16 1045 | Closed to all traffic | Monitor water levels | 12/17/2016 | 16/12/2016 17:13 p.m | Water Receeded |
| Naqali | Navutu Rd | Waimale Crossing | Flooded | 15/12/16 1045 | Open  | Monitor water levels | Unknown | 23/12/16 1630 | Water Receded |
| Naqali | Viria Rd | Wailase Crossing | Water receded | 15/12/16 1045 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Suva Sth | Latui Rd | Off Wailada Rd, after Metromix yard | Flooded | 15/12/16 1120 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1321 p.m | Water Receeded |
| Taunovo | Calia Rd |   | Flooded | 15/12/16 1120 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1010 a.m | Water Receeded |
| Taunovo | Wainadoi |   | Flooded | 15/12/16 1145 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1010 a.m | Water Receeded |
| Taunovo | Nabukavesi |   | Flooded | 15/12/16 1145 | Open to traffic | Monitor water levels | Unknown | 18-Dec-16 | Water level receded |
| Rewa | Raralevu Rd |   | Water receded | 15/12/16 1200 | Open | Monitor water levels | Unknown |   |   |
| Korovou | Navunisole Rd | Irish Crossing | Flooded | 15/12/16 1200 | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Suva Nth | Ratu Mara Rd | Near Namena Rd | Underslip, shoulder closed | 15/12/16 1200 | Road Open | Install bund to prevent further scour, close one lane | 12/21/2016 | 21/12/2016 0807 a.m | Temporary Fixed |
| Korovou | UN1542R Nawiwaivusa Rd | Off Nawiwaivusa Rd, known as Nakorovou Rd | Flooded | 15/12/16 1200 | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Rewa | Kings Rd | Verata area | Slip | 15/12/16 1230 | Road Open | Establishing to site, clear to shoulder | 12/16/2106 | 16/12/2106 1715 p.m | Landslip Cleared. |
| Rewa | Lakena Irrigation Rd |   | Flooded | 15/12/16 1230 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Korovou | Wairua Settlement Rd |   | Water receded | 15/12/16 1230 | Open | Monitor water levels |   | 12/17/2016 |   |
| Rewa | Wailoku Rd |   | Flooded | 15/12/16 1315 | Road open | Monitor water levels | 12/17/2016 | 17/12/2016 1538 p.m | Water Receeded |
| Naqali | Nabukaluka Rd | Waisomo Crossing | Water receded | 15/12/16 1400 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Rewa | Waila Treatment Plant Rd |   | Flooded | 15/12/16 1400 | Road Open | Road Open | 12/22/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Taunovo | Viwawa Rd |   | Flooded | 15/12/16 1430 | Closed to all traffic | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Taunovo | Nakaulevu Rd |   | Flooded | 15/12/16 1430 | Closed to all traffic | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Taunovo | Nasasa Rd |   | Flooded | 15/12/16 1430 | Closed to all traffic | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Taunovo | Waidova Rd |   | Flooded | 15/12/16 1430 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Taunovo | Tokotoko Rd |   | Flooded | 15/12/16 1430 | Closed to all traffic | Monitor water levels | 12/17/2016 | 17/12/2106 1010 a.m | Water Receeded |
| Naqali | Nataveya Rd | Waila Crossing | Flooded | 15/12/16 1430 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1236 p.m | Water Receeded |
| Rewa | Naliga Rd |   | Water receded | 15/12/16 1530 | Open | Monitor water levels |   | 12/17/2016 |   |
| Rewa | Buiduna Rd |   | Water receded | 15/12/16 1530 | Open | Monitor water levels | 16.12.16 |   |   |
| Naqali | Koroi Rd |   | Water receded | 15/12/16 1530 | Open  | Monitor water levels | Unknown | 22/12/16 1630 | Water receded |
| Taunovo | Vakabalea Rd |   | Flooded | 15/12/16 1600 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1010 a.m | Water Receeded |
| Taunovo | Veivatuloa Rd |   | Flooded | 15/12/16 1600 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1236 p.m | Water Receeded |
| Taunovo | Chevalier Rd |   | Flooded | 15/12/16 1600 | Road Open | Monitor water levels | 12/18/2016 | 17/12/2016 1236 p.m | Water Receeded |
| Taunovo | Wainadoi Village Rd |   | Flooded | 15/12/16 1600 | Road Open | Monitor water levels | 12/19/2016 | 17/12/2016 1236 p.m | Water Receeded |
| Rewa | Waituri Rd |   | Water receded | 15/12/16 1600 | Open | Monitor water levels | 12/20/2016 | 17/12/2016 1236 p.m | Water Receeded |
| Suva Nth | Davuilevu Farm Rd |   | Culvert undermined | 15/12/16 1700 | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1532 p.m | Culvert Installed and road reinstated. |
| Taunovo | Queens Rd | Before Wainigasau Junction. (RHS) Suva bound lane. | Land Slip | 16/12/2016 0636 a.m. | Half Road Closed. Drive with care. | Install signage for 1 lane open.Mobilisation for slip clearance. | 12/16/2016 | 16/12/2016 0859 a.m. | Landslip Cleared. |
| Taunovo | Queens Rd | Before Monfort Boys Town School | Land Slip | 16/12/2016 0636 a.m. | Road is open. Motorist to be cautious. | Install signage.Mobilisation for slip clearance. | 12/17/2016 | 16/12/2016 0859 a.m. | Landslip Cleared. |
| Suva North | Princess Rd |   | Land Slip | 16/12/2016 0636 a.m. | Road is open. Motorist to be cautious. | Install signage for 1 lane open.Mobilisation for slip clearance. | 12/16/2016 | 16/12/2016 0750am | Landslip Cleared. |
| Rewa | Toga Rd | Toga Crossing | Water receded | 16/12/2016 0636 a.m. | Open | Monitor water levels |   | 12/17/2016 |   |
| Rewa | Vuci South Rd |   | Flooding | 16/12/2016 0636 a.m. | Road Open | Monitor water levels | 12/20/2016 | 21/12/2016 0953 a.m | Water Receeded |
| Rewa | Vusuya rd |   | Flooding | 16/12/2016 0636 a.m. | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 0937 a.m | Water Receeded |
| Taunovo | Queens Rd |   | Land Slip | 16/12/2016 0717 a.m. | Open to traffic | Install signage.Mobilisation for slip clearance. | Unknown |   |   |
| Levuka | Ovalua Circular Road | Waidau Crossing | Flooding/Approach Washout | 16/12/2016 0717 a.m. | Open to Traffic | Monitor water levels | Unknown | 16/12/2016 1257 p.m | Water Receeded and debris cleared. |
| Korovou  | Dawasamu Rd |   | Road Washout | 16/12/2016 0717 a.m. | Road is open.  | Establish to site for road reinstatement | 12/16/2016 | 16/12/2016 1218 p.m | Road Reinstated |
| Korovou  | Waivou Dairy Farm Rd | Irish Crossing | Flooding | 16/12/2016 0725 a.m. | Closed to all traffic | Monitor water levels | Unknown | 12/18/2016 | Water Receded |
| Taunovo | Veivatuloa Rd |   | Overslip | 16/12/2016 0822 a.m. | Open to Traffic | Install signage.Mobilisation for slip clearance. | 12/17/2016 | 17/12/2016 1236 p.m | Slip Cleared |
| Naqali | Navutu Rd |   | Landslip | 16/12/2016 0940 a.m. | Open  | Mobilisation for slip clearance. | Unknown |   | Cleared |
| Rewa | Kings Rd | Verata Section | Landslip | 16/12/2016 1004 a.m. | Both Lane Open | Mobilisation for slip clearance. | 12/16/2106 | 16/12/2106 1715 p.m | Landslip Cleared. |
| Rewa | Nausori Bypass Rd | Infront of Pak & Save | Surface Flooding | 16/12/2016 1004 a.m. | Both Lane Open | Monitor water levels | 12/16/2106 | 16/12/2106 1715 p.m | Water Receeded |
| Rewa | Waila Feeder Rd |   | Water receded | 16/12/2016 1004 a.m. | Open | Monitor water levels | Unknown | 22/12/16 1630 | Water Receded |
| Rewa | Koronivia Rd |   | Flooding | 16/12/2016 1041 a.m. | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 0842 a.m | Water Has Receeded |
| Naqali | Waibau Rd | Waibau bridge | Flooded | 15/12/16 1030 | Closed to all traffic | Monitor water levels | 12/16/2016 | 16/12/2016 0818am | Water Has Receeded |
| Rewa | Ratu Kadavulevu Rd | Nakelo - Kuku Rd Section | Flooding | 16/12/2016 1046 a.m. | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Rewa | Loganisebi Rd |   | Landslip | 16/12/2016 1056 a.m. | Road Open | Mobilisation for slip clearance. | 12/23/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Rewa | Loganisebi Rd | Crossing | Flooding | 16/12/2016 1056 a.m. | Road Open | Monitor water levels | 12/24/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Rewa | Baulevu Rd |   | Fallen FEA Power Pole | 16/12/2016 1106 a.m. | Road is Open | Relevant authority being notified (FEA) | 12/25/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Rewa | Nalase Rd | Nabuli Village/Nalase Village/Vunisinu Village/Nakorovou Village/Nadoria Village | Flooding | 16/12/2016 1125 a.m. | Closed to all traffic | Monitor water levels | 12/22/2016 | 22/12/2016 1056 a.m | Water Receeded |
| Naqali | Sawani Serea Rd |   | Slump/Pavement Crack | 16/12/2016 1125 a.m. | Open to traffic | Establishment to site | Unknown |   | Crack sealed |
| Naqali | Sawani Serea Rd |   | Slump/Pavement Crack | 16/12/2016 1125 a.m. | Open to traffic | Establishment to site | Unknown | 12/18/2016 | Backfilled under slip  |
| Suva Sth | Wailea St | Off Fletcher Rd | Flooding | 16/12/2016 1152 a.m. | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Rewa | Noco Delta Rd |   | Flooding | 16/12/2016 1205 p.m. | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Rewa | Sandhurst St |   | Flooding | 16/12/2016 1211 p.m. | Road Open | Monitor water levels | 12/17/2016 | 17/12/2016 1010 a.m | Water Has Receeded |
| Suva Sth | Benau St |   | Culvert Collapsed | 16/12/2016 1417 p.m. | Open to one lane  | Continue reinstatement | Unknown |   |   |
| Naqali | Nasiriti Rd |   | Culvert undermined | 16/12/2016 1422 p.m. | Closed to all traffic | Mobilisation for reinstatement works. | Unknown |   |   |
| Naqali | Wailoa Rd |   | Landslip | 16/12/2016 1429 p.m. | Open to one lane traffic. | Mobilisation for slip clearance works. | 12/17/2016 | 17/12/2016 1054 a.m | Landslip Cleared. |
| Naqali | Sawani Serea Rd |   | Culvert Headwall Washout | 16/12/2016 1429 p.m. | Open to traffic. Motorist to be cautious. | Warning Signs set up | Unknown |   | To be repaired during routine works |
| Taunovo | Nabukavesi Rd |   | Road Drop | 16/12/2016 1729 p.m. | Closed to Traffic | Geotech input required. | Unknown |   | Road closed signs in place. No further action from FHH at this time. |
| Rewa  | Naduru Rd |   | Flooding | 16/12/2016 1729 p.m. | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 0939 a.m | Water Receeded |
| Rewa  | Waidamudamu Feeder Rd |   | Flooding | 16/12/2016 1729 p.m. | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 0939 a.m | Water Receeded |
| Rewa  | Waikete Road |   | Water receded | 12/17/2016 7:00 | Open | Monitor water levels | Unknown | 23/12/16 0700 | Water Receded |
| Korovou | Naboro Cocoa Rd | Delekado Crossing | Flooding | 17/12/2016 1027 a.m | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Naqali | Nairukuruku Rd | Waima Crossing | Water receded | 17/12/2016 1304 p.m | Open | Monitor water levels | Unknown |   | Water receded |
| Naqali | Wailoa Rd | Matainasau Crossing | Approach washout | 17/12/2016 1304 p.m | Open, proceed with caution | Monitor water levels | 12/30/2016 | 28/12/16 1630 | Slip Cleared |
| Taunovo | Veivatuloa Rd |   | Landslip | 17/12/2016 1356 p.m | Open to traffic | Install signage.Mobilisation for slip clearance. | Unknown | 12/18/2016 | Removed slip debree |
| Taunovo | Veivatuloa Rd |   | Landslip | 17/12/2016 1356 p.m | Open to traffic | Install signage.Mobilisation for slip clearance. | Unknown | 12/18/2016 | Removed slip debree |
| Naqali | Sawani Serea Rd |   | Fallen tree | 17/12/20161948 p.m | Open to traffic | Tree to be removed | 12/18/2016 | 12/18/2016 | Trees removed |
| Rewa | Toga Rd |   | Water receded | 17/12/20162300 p.m | Road open | Monitor water levels | 12/22/2016 | 22/12/2016 0810 a.m | Water Receeded |
| Rewa | Cautata Rd |   | Flooding | 18/12/2016 0500 a.m | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 1423 p.m | Water Receeded |
| Korovou | Kings Rd | Wailetua | Flooding | 18/12/20160500 a.m | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Korovou | Kings Rd | Korovou Town | Flooding | 18/12/20160500 a.m | Open for traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Korovou | Londoni Rd | Londoni | Fallen Trees | 18/12/20160555 a.m | Open to traffic | Trees to be removed | 12/18/2016 | 12/18/2016 | Trees removed |
| Korovou | Dawasamu Rd | Qelekro crossing | Flooding | 18/12/20160555 a.m | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Korovou | Nawiwaivusa Rd |   | Water receded | 18/12/20160555 a.m | Open to traffic | Monitor water levels | Unknown | 22/12/16 1000 | Water level receded |
| Korovou | Nasabitu Rd | Waisa Crossing | Water receded | 18/12/20160555 a.m | Open to traffic | Monitor water levels | Unknown | 22/12/16 1000 | Water level receded |
| Korovou | Wailatua Village Rd |   | Open | 18/12/20160555 a.m | open  | Monitor water levels |   | 22/12/16 1630 |   |
| Levuka | Ovalua Circular Road | Temporary Crossing | Crossing washed out | 18/12/20160605 a.m | Open | Monitor water levelRepair crossing once water level receded | Unknown |   |   |
| Rewa | Kings Rd | Kasavu | Landslip | 18/12/2016 0640 a.m. | Both lanes closed to heavy vehicles except light vehicles only. | Monitor further slippingErrect Temp Traffic Signs | Unknown |   |   |
| Naqali | Sawani Serea Rd | Naqali Bridge | Underwater | 18/12/2016 0650 a.m. | Road open | Monitor water levels | 12/22/2016 | 23/12/2016 0805 a.m | Water Receeded |
| Naqali | Veria Rd | Off Sawani Serea Rd | Water receded | 18/12/2016 0650 a.m. | Open | Monitor water levels | Unknown |   | Water receded |
| Korovou | Londoni Rd | Londoni | Flooded | 18/12/20160740 a.m | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Naqali | Buiduna Rd |   | Flooded | 18/12/20160740 a.m | Road open | Monitor water levels | 12/22/2016 | 23/12/2016 0805 a.m | Water Receeded |
| Naqali | Waila Rd | Waila , Nausori | Water receded | 18/12/20160740 a.m | Open | Monitor water levels | Unknown |   | Water receded |
| Naqali | Sawani Serea Rd | After Savu Rd | Under Slip | 18/12/2016 0750 a.m. | Open to traffic - Caution when crossing  | Errect Temp Traffic Signs | Unknown | 12/18/2016 | Under slip back filled |
| Korovou | Kings Rd | Navieweiwali Crossing  | Underwater | 18/12/2016 0800 a.m. | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Korovou | Kings Rd | Naqia Bridge | Underwater | 18/12/2016 0800 a.m. | Open to traffic | Monitor water levels | Unknown | 12/18/2016 | Water level receded |
| Rewa | Loganisebi Rd | Off Kings rd, Kasavu | Bridge approaches washed out | 18/12/2016 0830 a.m. | Road Open | Backfill Approaches | 12/19/2016 | 19/12/2016 0918 a.m | Bridge Approaches reinstaded. |
| Nagali | Sawani Serea Rd |   | Fallen tree | 18/12/2016 0835 a.m. | Open to traffic | Remove tress | 12/18/2016 | 12/18/2016 | Tree removed |
| Taunovo | Queens rd | Veisari | Land Slip | 18/12/2016 0900 a.m. | One lane closed | Remove slip debree | 12/18/2016 | 12/18/2016 | Removed slip debree |
| Naqali | Savu Rd | Savu Bridge 1, Shantiketan Primary School | Water receded | 18/12/2016 0900 a.m. | Open | Monitor water levels | Unknown |   | Water receded |
| Korovou | Namara Rd |   | Water receded | 18/12/2016 0930 a.m. | Open | Monitor water levels | Unknown | 22/12/16 1000 | water receded |
| Rewa | Namara Rd |   | Land Slip | 18/12/2016 0930 a.m. | One lane closed | Remove slip debree | Unknown |   | Open to all traffic, slip to be removed during routine works. |
| Ovalau | Ovalau circle road | Vuma Crossing | Temporary crossing wash out | 18/12/2016 1100 a.m. | Open for traffic | Backfill Crossing | Unknown | 12/18/2016 | Backfilled wash out |
| Ovalau | Ovalau circle road | Rukuruku crossing | Appraoches wash out | 18/12/2016 1100 a.m. | Open to traffic | Backfill Crossing | Unknown | 12/18/2016 | Approaches backfilled |
| Ovalau | Ovalau circle road | Natokalau | Land slip | 18/12/2016 1100 a.m. | Open to traffic | Remove slip debree | Unknown | 12/18/2016 | Removed slip debree |
| Ovalau | Ovalau circle road | Bureta bridge | Approaches wash out | 18/12/2016 1100 a.m. | Open to traffic | Backfill Approaches | Unknown | 12/18/2016 | Approaches backfilled |
| Ovalau | Ovalau circle road | Wainaloka | Land Slip | 18/12/2016 1100 a.m. | Open to traffic | Remove slip debree | Unknown | 12/18/2016 | Removed slip debree |
| Rewa | Princess Rd |   | Flooding | 18/12/2016 1120 a.m. | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 0841 a.m | Water Receeded |
| Taunovo | Nabukavesi |   | Land slip | 18/12/2016 1125 a.m. | Closed to traffic | Geotech input required. | Unknown |   | Road closed signs in place. No further action from FHH at this time. |
| Rewa | Koronivia Rd | Koronivia Town | Flooding | 18/12/2016 1215 p.m. | Road Open | Monitor water levels | 12/22/2016 | 23/12/2016 0805 a.m | Water Receeded |
| Taunovo | Namosi Rd |   | Land slip | 18/12/2016 1255 p.m. | Cleared | Remove slip debree | 12/19/2016 | 12/23/2016 |   |
| Naqali | Sewani Serena Rd |   | Land Slip | 18/12/2016 1300 p.m. | Open to traffic | Remove slip debree | 12/18/2016 | 12/18/2016 | Removed slip debree |
| Taunovo | Namosi Rd | Wainikovu Crossing | Approach wash out | 18/12/2016 1325 p.m. | One lane closed | Accessable | 12/19/2016 | 12/23/2016 |   |
| Korovou | Naboro Cocoa Rd | Delekado Crossing | Water receded | 12/18/2016 | open | Monitor water levels | Unknown | 22/12/16 1000 |   |
| Korovou | Dawasamu Rd | Nabolau | Flooded | 18/12/201614:50 | Open to traffic | Monitor water levels | Unknow | 12/18/2016 | Water level receded |
| Taunovo | Namosi Rd |   | Land slip | 18/12/2016 1500 p.m. | Open | Remove slip debree | 12/19/2016 | 12/23/2016 | Cleared |
| Rewea | Raralevu Rd |   | Flooded | 18/12/20161700 p.m | Road Open | Monitor water levels | 12/21/2016 | 21/12/2016 0910 a.m | Water Receeded |
| Korovou | Kings Rd | Wainibuka Area | Flooded | 18/12/20161700 p.m | Clossed to traffic | Monitor water levels | Unknown | 19/12/20160700 a.m | Water Receeded |
| Korovou | Dawasamu Rd | Qelekoro Crossing | Flooded | 19/12/20160700 a.m | Road Open | Monitor water levels | 12/20/2016 | 20/12/2016 1423 p.m | Water Receeded |
| Korovou | Vunidawa Rd (Tailevu) | Off Kings Rd | Open | 19/12/20160655 a.m | Open | Monitor water levels | Unknown | 22/12/16 1000 |   |
| Naqali  | Sawani Serea Rd | Savu Flat | Flooded | 19/12/20160655 a.m | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Naqali  | Wailoa Rd | Naivucini Crossing | Approach Washout | 19/12/20160718 a.m | Road Open | Monitor water levels | Unknown | 22/12/16 1630 | Approaches backfilled |
| Rewa | Navuso Rd |   | Flooded | 19/12/20160728 a.m | Road open | Monitor water levels | 12/21/2016 | 21/12/2016 1012 a.m | Water Receeded |
| Rewa | Jalim Avenue Rd |   | Flooded | 19/12/20160728 a.m | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Rewa | Nakini Rd |   | Flooded | 19/12/20160728 a.m | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Rewa | Noco Delta Rd |   | Flooded | 19/12/20160741 a.m | Road Open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Naqali | Qiolevu Rd |   | Underslip | 19/12/20160809 a.m | Road Open | Install signage.Mobilisation for construction of a temporary Detour lane. | 12/19/2016 | 19/12/2016 1438 p.m | Construction of detour lane completed and gravelled. |
| Korovou | Wairua Settlement Rd |   | Water receded | 19/12/2016 0821 a.m | Open | Monitor water levels | Unknown | 12/22/2016 | Water Receded |
| Naqali | Nakadi Rd |   | Water receded | 19/12/2016 1038 a.m | Open | Monitor water levels | Unknown |   | Water receded |
| Rewa | Veisama Rd |   | Flooded | 19/12/2016 1343 p.m | Road open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Rewa | Dravo Rd |   | Flooded | 19/12/2016 1437 p.m | Road open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Naqali | Lutuvuisiga Rd | Wainivida Crossing | Water receded | 19/12/2016 1448 p.m | Open to one lane | Monitor water levels | Unknown |   | Water receded |
| Naqali | Muavesi Rd |   | Side Slip | 19/12/2016 1448 p.m | Open to one lane | Mobilisation for repair works. | Unknown |   |   |
| Naqali | Naisole Rd |   | Water receded | 19/12/2016 1448 p.m | open | Monitor water levels | Unknown |   | Water receded |
| Korovou  | Kings Rd | Bucalevu Bridge | Flooded | 19/12/2016 1523 p.m | Road Open | Monitor water levels | 12/20/2016 | 20/12/2016 1123 p.m | Water receeded |
| Korovou  | Kings Rd | Wailotua Flats | Flooded | 19/12/16 1730pm | Closed to all Traffic | Monitor water levels | 12/20/2016 | 20/12/2016 1123 p.m | Water receeded |
| Rewa | Baulevu Rd |   | Flooded | 19/12/2016 1448 p.m | Closed to all Traffic | Monitor water levels | Unknown |   |   |
| Rewa | Nasali Rd |   | Flooded | 19/12/2016 1448 p.m | Road open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Naqali | Nakorosule Rd | Waibalavu Crossing | Washout crossing approach | 20/12/16 1344pm | Open to 4x4 via wet crossing | Ford in place, backfillling approaches | Unknown |   | Temporary ford pushed through |
| Rewa | Rarabici Rd |   | Washout crossing approach | 20/12/16 1538 p.m | Road open | Monitor water levels | 12/22/2016 | 22/12/2016 0812 a.m | Water Receeded |
| Taunovo | Saliadrau Rd |   | Landslide | 20/12/2016 1632 p.m | Open | Establishment to site for clearing works | Unknown | 23/12/16 1700 | Slip Cleared |
| Taunovo | Namuamua Rd | Namado Gorge | Partly Washout | 20/12/16 1500 | Open | Establishment to site for re instatement works | Unknown |   | Backfilled  |
| Taunovo | Namuamua Rd | Wainiyavu Crossing | Approach Washout | 20/12/2106 1632 p.m | Open | Establishment to site for clearing works | 24/12/16 1630 | 24/12/16 1630 | Approaches backfilled |
| Naqali | Vunidawa Rd | Vunidawa Bridge | Approach Washout | 21/12/2016 1527 pm. | Road Open | Establishment to site for reinstatement works | 12/22/2016 | 22/12/2016 1304 p.m | Aprroach Reinstated |
| Naqali | Wailoa rd | Waimalua Crossing | Approach Washout | 21/12/2016 1527 pm. | Open | Establishment to site for reinstatement works | Unknown | 22/12/16 1630 | Approaches backfilled |
| Naqali | Nabukaluka Rd |   | Underslip | 21/12/2016 1527 pm. | Road open, motorist travel with caution. | Establishment to site for reinstatement works | Unknown |   |   |
| Naqali | Walioa Rd | Past Laselevu Village | Slips | 29/12/16 1310 | Closed | Clearing works in progress | Unknown |   |   |
| Naqali | Nadovou Nasali Rd | To be confirmed | To be confirmed | 30/12/16 0700 | Closed | Inspection underway, then clearing | Unknown |   |   |
| Naqali | Laselevu Rd | Bus turning point | Debris on carriageway | 30/12/16 1500 | Closed | Clearing works in progress | Unknown |   |   |
| Naqali | Nakorosule Rd |   | Landslip | 30/12/16 1500 | Closed | Clearing works in progress | Unknown |   |   |
| Naqali | Sawanikula Bukunivatu Rd |   | Washout crossing approach | 30/12/16 1500 | Closed | Clearing works in progress | Unknown |   |   |
| Naqali | Nuku Village Rd |   | Washout crossing approach | 30/12/16 1500 | Closed | Clearing works in progress | Unknown |   |   |

**WESTERN DIVISION**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Depot | Road Name | Location Description | Status of Damage | Time/Date Reported | Advice to Motorists | FRA Contractors Action that Will be Taken | Expected Road Opening Date | Time/Date Resolved | How Resolved |
| Rakiraki | Kings Rd | Between the new Chinese Bridge and the Flying Prince Service station. | Flooding  | 19/12/2016 11am | Open to all Traffic  |   |   | 20/12/2016 7am |   |
| Rakiraki | Akbar Street | Rakiraki Town | Flooding | 20/12/2016 7am | Open to all Traffic  |   | 12/20/2016 | 12/20/2016 |   |
| Rakiraki | Waimari Road  | Qalau  | Flooding | 20/12/2016 7am | Open to all Traffic  |   | 12/20/2016 | 12/20/2016 |   |
| Rakiraki | Korotale V/Road | Naqoro Flat | Flooding | 20/12/2016 7am | Open to all Traffic  |   | 12/20/2016 | 12/20/2016 |   |
| Rakiraki |   | Nubumakita Rd / crossing | Landslip | 31/12/2016 11.00am | Closed to all traffic | Moblise plant to clear Landslip & Backfill approach  | 1/5/2017 |   |   |
| Rakiraki | Ganilau Road | Ganilau Road | Landslip | 22/12/16 9.30am | Open to all Traffic  |   |   | 12/23/2016 | clear landslide |
| Rakiraki | Nabalabala Road |   | Landslip | 22/12/16 9.30am | Open to all Traffic  |   |   | 22/12/2016 6pm | Backfill aproach and clearing debris  |
| Rakiraki | Lawaki/Nasau Road  | Nasau Crossing  | Approach Washout, Debris and Silt | 22/12/16 9.30am | Open to all Traffic  |   |   | 28/12/2016 5pm | Backfill aproach and clearing debris  |
| Rakiraki | Nasau Road  | Nawairuku Crossing | Approach Washout, Debris and Silt | 22/12/16 9.30am | Closed to all traffic | Work in progress. Backfill aproach and clearing debris  | 1/5/2017 |   |   |
| Rakiraki | Nauria Road | Crossing | Approach Washout | 22/12/16 9.30am | Open to all Traffic,  | Work in progress |   | 27/12/2016 5pm | Backfill aproach and clearing debris  |
| Rakiraki | Vanuakula Road | Crossing | Approach Washout | 22/12/16 9.30am | Open to all Traffic  | Work in progress |   | 27/12/2016 5pm | Backfill aproach and clearing debris  |
| Rakiraki | Wailevu Road | Crossing | Approach Washout / culvert damaged  | 22/12/16 9.30am | Open to all Traffic  |   |   | 22/12/2016 6pm | Clear debris and backfill washout with metal  |
| Rakiraki | Vatukacevaceva Rd  |   | Drop Out/ Landslips/ approach washout  | 22/12/16 9.30am | Open to all Traffic  | work in progress | 12/28/2016 |   | Clear debris & landslips and backfill washout with metal  |
| Rakiraki | KINGS ROAD | Tobu Village | Clear Detritus / Debris | 20/12/2016 2:00pm | Open to all Traffic  |   |   | 12/22/2016 | clear silt and debris |
| Rakiraki | Korotale Valley Rd  | Crossing  | Approach washout/ Deck damaged | 21/12/2016 12pm | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Barotu Road  | Barotu Crossing 1 | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki |   | Barotu Crossing 2 | Approach washout | 21/12/2016 9am | Open to all Traffic  |   |   | 12/23/2016 | Backfill aproach and clearing debris  |
| Rakiraki |   | Naboulini Village  | Landslip/ Flooding  | 20/12/2016 8.00am | Road is open to traffic, but drive with caution as mud and debris is being cleared from the road  | Work in progress  | 12/31/2016 |   |   |
| Rakiraki | Kings Rd | Mataiwailevu  | Landslip | 20/12/2016 12pm | Open to all Traffic  |   |   | 22/12/2016 5pm | Remove Landslip and clear debris  |
| Rakiraki | Kings Rd | Near new Rakiraki Bridge  | Pavement washout  | 20/12/2016 12pm | Open to all Traffic  |   |   | 22/12/2016 5pm | Repair Pavement  |
| Rakiraki  | Ganillau Rd | Maniava Crossing, Approach Washout  | Flooding  | 19/12/2016 7am | Open to all Traffic  | Moblise plant to backfill Approach once Barotu rd is open  | 12/22/2016 |   |   |
| Rakiraki | Nailuva Road | Burelevu Crossing | Flooding , Metal is washed out  | 19/12/2016 7am | Open to all Traffic  |   |   | 24/12/16 5pm | Backfill Approach with metal, put boulders and clear debris  |
| Rakiraki | Nakorotubu Rd  | Mataso Crossing 1  | Flooding, Approach washed out  | 18/12/2016 3pm | Open to all Traffic  |   |   | ############# | Backfill Approach with metal and clear debris  |
| Rakiraki | Nanokonoko Rd  | Nanokonoko Crossing 1 & 2 | Flooding, Approach washed out  | 18/12/2016 3pm | Open to all Traffic  | work in progess | 28/12/2016 5pm |   | Backfill Approach with metal and clear debris  |
| Rakitaki | Naqoro Rd  | Naqoro Flat | Flooding | 18/12/2016 10am | Open to all Traffic  | Water Level jas receded, still need to montior in the next high tide  | 12/18/2016 |   |   |
| Rakiraki | Namonamo Road | crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Burenitu Road  | Burenitu Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Waimari Road  | Qalau Flat  | Flooding | 19/12/2016 7am | Close to all traffic | Water Level still high, waiting to recede | 12/20/2016 |   |   |
| Rakiraki | Rakiraki Access | FSC Flat | Flooding | 18/12/16 - 12.30am | Open to all traffic |   | 12/18/2016 |   |   |
| Rakiraki | Korotale V/Road | Town Bridge | Flooding | 20/12/2016 8.30am | Open to traffic, but take caution as debris and mud is still being cleared  | Clearing debris and make roads accessable  | 12/20/2016 | ############# |   |
| Rakiraki | Katudrau Road | Katudrau Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Korotale V/Road | Drana Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | ############# | Backfill aproach and clearing debris  |
| Rakiraki | Narara Road  | Narara Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Katudrau Road | Katudrau Crossing | Road open | 15/12/16=2.30pm | Open to All Traffic |   | 12/15/2016 |   |   |
| Rakiraki | Waimari Road | Qalau Flat | Road open | 15/12/16=2.30pm | Open to All Traffic |   | 12/15/2016 |   |   |
| Rakiraki | Narara Road | 4 Crossing | Road open | 15/12/16=2.30pm | Open to all traffic |   | 12/15/2016 |   |   |
| Rakiraki | Lau Road | Ford Crossing | Flooding | 19/12/2016 7am | Closed to all traffic | Work in progress.Backfill approach with Metal and clear debris  | 1/5/2017 |   |   |
| Rakiraki | Nausori Road | Ford Crossing | Flooding | 19/12/2016 7am | Closed to all traffic | Work will start once Lau rd Ford crossing is open.Backfill approach with Metal and clear debris  | 1/5/2017 |   |   |
| Rakiraki | Bainisoqosoqo Road | Crossing | Flooding | 18/12/16 - 3.00pm | open to all traffic  | Water Level still high, waiting to recede | 12/19/2016 |   |   |
| Rakiraki | Vunikavikaloa Road | Crossing | Flooding | 18/12/16 - 3.00pm | Open to all traffic  | Water Level still high, waiting to recede | 12/19/2016 | 18/12/2016 3pm |   |
| Rakiraki | Dreketi Rd | Dreketi crossing | Flooding | 18/12/16 3pm | Open to all Traffic  |   |   | 12/18/2016 |   |
| Rakiraki | Burenitu Road | Burenitu Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Rakiraki | Vitiri Road  | Vitiri Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Tavua  | Nadelei Rd  | Right side  | Fallen tree  | 17/12/2016 9.30am | Open to all Traffic  |   |   | 17/122016 5pm | Cut and clear tree from Road |
| Tavua  | Nadolodolo Rd  |   | Flooding  | 19/12/2016 2.30pm | Open to all Traffic  |   |   | 12/23/2016 | Water receded |
| Tavua  | Naseyani Rd |   | Flooding, Approach washed out  | 19/12/2016 10.30am  | Open to all Traffic  |   |   | 12/23/2016 | Water receded |
| Tavua  | Mataniwai Rd-Flat |   | Flooding | 19/12/2016 10.30am  | Open to all Traffic  |   |   | 12/21/2016 |  Grading and Resheeting  |
| Tavua  | Mataniwai Bridge  |   | Flooding | 19/12/2016 10.30am  | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Tavua  | Qalela |   | Surface washout  | 19/12/2016 10.30am  | Open to all Traffic  |   |   | 12/21/2016 | Backfill with metal |
| Tavua  | Qalela 2 |   | Flooding  | 19/12/2016 10.30am  | Open to all Traffic  |   | \ | 12/21/2016 | Approach backfilled with metal  |
| Tavua  | Matacawa Rd  |   | Culvert Crossing damaged | 19/12/2016 10.30am  | Open to all Traffic  | Work in progress Backfill approach & Clear debris  | 12/22/2016 | 12/21/2016 | Backfill aproach and clearing debris  |
| Tavua | Lakalaka | Lakalaka Crossing | Flooding- Approach washout  | 18/12/16 10am | Open to all Traffic  | Backfill approach & Clear debris  | 12/21/2016 | 12/21/2016 | Backfill aproach and clearing debris  |
| Tavua | Vuqele Rd | Vuqele Crossing | Flooding | 19/12/2016 7am | Open to all Traffic  | Plant will be mobilised to backfill approach & Clear debris  |   | 12/23/2016 | Water receded  |
| Ba  | Koula Rd  | Pass bula bula school | Flooding | 19/12/2016 12.30pm | Open to all traffic. | Water Level is high, with strong currents. waiting to recede |   |   |   |
| Ba  | Ebuto Rd  | Ebuto Crossing  | Flooding | 17/12/2016 10.00am | Closed to all traffic | Water Level still high, waiting to recede | 12/19/2016 |   |   |
| Tavua  | Dramasi Rd | Dramasi Crossing  | Approach washout  | 19/12/2016 10.30am  | Open to all traffic  | Backfill approach & Clear debris  | 12/22/2016 |   |   |
| Ba  | Babriban Rd  | Babriban Crossing  | Flooding, Approach washed out  | 20/12/2016 8am | Open to all traffic. | Approach has been repaired  |   | 12/20/2016 |   |
| Ba  | Kotoboya Rd  | koroboya no 1 crossing | Flooding, Approach washed out  | 20/12/2016 7am | Open to all traffic. | Approach has been repairs  |   | 12/20/2016 |   |
| Ba  | Varodoli Rd  | Varandoli crossing | Flooding | 19/12/2016 12.00pm | open to all traffic  | Water Level is high. waiting to recede |   |   |   |
| Ba  | Cemetery Rd | Varandoli Cemetery Rd | Flooding | 19/12/2016 11.00am | open to all traffic  | Water Level is high. waiting to recede |   |   |   |
| Ba  | Navala St  | Yaloku Crossing  | Flooding | 18/12/2016 5pm | Open to all Traffic  |   |   | 12/23/2016 | Backfill aproach and clearing debris  |
| Ba | Toge Rd | 1st Crossing | Flooding |  20/12/16 8am | Open to all Traffic  |   |   | 12/21/2016 | Water receded  |
| Ba  | Navala St  | Navala Crossing  | Flooding | 19/12/2016 7am | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Nadi  | Arolevu Rd  | Arolevu Crossing  | Flooding | 18/12/16 10am | Open to all Traffic  | Water Level is receding but need to montior in the next high time | 12/18/2016 |   |   |
| Lautoka  | Vakabuli Ind Sch Rd | Vakabuli Ind Sch Rd | Flooding | 19/12/2016 2pm | Open to all Traffic  | Waiting for Water Level to recede then carry out inspection of damages | 12/20/2016 |   |   |
| Nadi  | Sabeto rd  | Lidilidi Crossing  | Flooding | 19/12/2016 2pm | Open to all Traffic  | Moblise plant to clear Debris from crossing and decking  |   |   |   |
| Nadi  | Wailoko Rd  | Wailoko Rd  | Flooding  | 19/12/2016 2.30 pm | Open to all Traffic  | Road is open  | 12/20/2016 |   |   |
| Nadi  | Namulomulo Road  | NAMULOMULO VILLAGE LOW LEVEL BRIDGE | Flooding, approach washed out, debris on deck  | 21-Dec-16 | Open to all Traffic  |   |   | 12/23/2016 | approach backfilled and clearing debris  |
| Nadi  | Nadele Rd | Nadele Crossing  | Flooding.CONCRETE DECKING DAMAGED AND INLET OF CROSSING BLOCKED BY FALLEN TREE TRUNK. | 20/12/2016 4pm | Open to all Traffic  |   |   | 12/21/2016 | Backfill aproach and clearing debris  |
| Nadi  | Bukuya Rd  | Nasivikoso Crosing | Flooding | 19/12/2016 7.30am | Open to all Traffic  |   |   | 12/23/2016 | Backfill approach and put boulders |
| Nadi  | Savalau Rd  | Savalau Crossing  | Flooding  | 18/12/2015 9.30am | Open to traffic  | Debris on decking needs to be cleared  | 12/19/2016 | 12/19/2016 |   |
| Nadi  | Bukuya Rd | 300m past Junction to Magnessium Mine Access Rd. | Road drop Out  | 23/12/2016 8.30am | Open to traffic . Drive with caution  | Backfill & compact with geofabric. Do Rock-Protection works at edges of fill. | 1/9/2017 |   |   |
| Sigatoka | Valley Road | Pass Nukuilau Nursing Station | Both Approaches washed out. | 16/12/2016 10.00am | Open to all traffic  | Work in progress | 29/12/2016 5pm |   | Backfill approaches and clear debris |
| Sigatoka  | Queens Road  | Near Namatakula Village | Road Drop Out | 17/12/16 8.30am | Open to all traffic  | Barricaded with safety Netting for public/ motorist safety  | 12/18/2016 |   |   |
| Sigatoka | Tilivalevu Rd | Qwali Flat | Flooding  | 18.12.2016 11am | Open to all traffic  | Grading and resheeting |   | 12/23/2016 | Water receded  |
| Sigatoka | Valley Rd | Matewale crossing | Flooding  | 18.12.2016 3pm | Open to all traffic  |   |   | 12/22/2016 | Backfill Approach with metal and clear debris  |
| Sigatoka | Nacocolevu Rd | Lawai Crossing | Flooding  | 18.12.2016 3pm | Open to all traffic  |   |   | 12/21/2016 | Water level receded  |
| Sigatoka | Balenabelo Rd | Ford Crossing after Balenabelo Village | Flooding  | 18.12.2016 5pm | Open to all traffic  |   |   | 12/23/2016 | Water level receded  |
| Sigatoka | Valley Rd | Narewa | Flooding, | 19/12/2016 6pm | Open to all traffic  |   | 12/22/2016 | 12/21/2016 | Water level receded  |
| Sigatoka | Valley Rd | Narata Flat | Flooding | 19/12/2016 6pm | Open to all traffic  |   | 12/22/2016 | 12/21/2016 | Water level receded  |
| Sigatoka | Valley Rd | 300 M pass Nalebaleba | Flooding,Road washout | 19/12/2016 6pm | Temporary bypass road is open to traffic  | Plant is carrying out the repair works  | 12/21/2016 |   | Water level receded  |
| Sigatoka | Queen's Rd | Sigatoka Town Start | Flooding,Underwater by 0.5 M | 20/12/2016 6.30 Am | Open to all traffic  | Waiting for Water Level to recede then carry out inspection of damages |   |   | Water level receded  |
| Sigatoka | Valley Rd | Kedrakulu | Flooding | 20/12/2016 6.30 Am | Open to all traffic  |   | 12/22/2016 |   | Water level receded  |
| Sigatoka | Kavanagasau Rd | Laselase Bridge | Flooding, | 20/12/2016 6.30 Am | open to all Traffic  | Carry out inspection of damages  |   |   | Water level receded  |
| Sigatoka | Nabaka Rd | Nabaka Bridge | Flooding  | 20/12/2016 10.30 Am | Open to all traffic  |   | 12/22/2016 |   | Water level receded  |
| Sigatoka | Kavanagasau Rd | Naroro | Flooding  | 20/12/2016 10.30 Am | Open to heavy vehicles only | Waiting for Water Level to recede then carry out inspection of damages | 12/22/2016 |   | Water level receded  |
| Sigatoka | Kavanagasau Rd | Raiwaqa Crossing | Flooding  | 20/12/2016 3.30 pm | Open to all Traffic  |   |   | 12/21/2016 | Water level receded  |
| Sigatoka | Bukuya Rd | Tavasa Hill | Landslip | 21/12/2013 6.40pm | Open to all Traffic  |   |   | 12/22/2016 | Landslip cleared  |
| Sigatoka | Kavanagasau Rd | Pass Vunarewa | Landslide  | 21/12/2013 3pm | Open to all Traffic  |   |   | 12/23/2016 | Landslip cleared  |
| Sigatoka | Nakoro Rd  |   | Landslide, Road Drop out  |  24/12/16 | Open to all Traffic  |   |   |   | Clear Landslide and backfill drop outs  |

**NORTHERN DIVISION**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Depot** | **Road Name** | **Location Description** | **Status of Damage** | **Time/Date Reported** | **Advice to Motorists** | **FRA Contractors Action that Will be Taken** | **Expected Road Opening Date** | **Time/Date Resolved** | **How Resolved** |
| Natua | Nabouwalu - Daria | Vacikadrodro Crossing | Approach Washout | 6:00am 14/12/16 | Open to all traffic | Reinstate Washout once water receded | 12/14/2016 | 6:00pm 14/12/16  | Completed |
| Taveuni | North Coastal Rd | Waibula Bridge | Underwater | 7:00am 14/12/16 | Open to all traffic | Wait for water to recede | 12/14/2016 | 6:00pm 14/12/16  | Completed |
| Taveuni | South Coastal | 9km to 12km - Ura Hill | Scoured wheel tracks | 12:00pm 14/12/16 | Open to all traffic | Trim windrow, fill scour, cut outs | 12/14/2016 | 6:00pm 14/12/16  | Completed |
| Labasa | Wainikoro | 24km | Red Clay visible, may turn into depression | 12:00pm 14/12/16 | Open to all traffic | Digout and replace with suitable material | 12/14/2016 | 6:00pm 14/12/16  | Completed |
| Savusavu | Kubulau Peninsular Rd | 15.831km | Depression, heavy wheel tracks | 11.30am 16/12/16 | Open to all traffic | Digout and replace with suitable material | 12:00pm 20/12/16 | 8:00am 22/12/16 | Completed |
| Taveuni | North Coastal Rd | Waibula Bridge | Underwater | 7:00am 17/12/16 | Open to all traffic | Continue to monitor water levels |   | 8:00am 22/12/16 | Completed |
| Taveuni | South Coastal | Ura Flat | Underwater | 7:00am 17/12/16 | Open to all traffic | Wait for water to recede | 12/17/2016 | 4:00pm 17/12/16 | Completed |
| Savusavu | Bucabay | 56km Bagasau | Land slide | 9:45am 17/12/16 | Open to all traffic | Clear Landslide | 12/17/2016 | 3.30pm 17/12/16 | Completed |
| Savusavu | Bucabay | 52km Kasavu Flat  | Underwater | 10.50am 17/12/16 | Open to all traffic | Wait for water to recede | 12/17/2016 | 4:00pm 17/12/16 | Completed |
| Natua | Muanidevu Road  | Muanidevu Road  | Aggregate washed away and has become slippery for Buses. | (PEL Email to FRA 17/12/16 at 4:55pm) | Restricted/Delayed Bus Services | Inspect & program repairs once TD04F finishes | TBC |   | Pending |
| Natua | Vatubogi Road | Road from Coboi ahead to the end is muddy | Aggregate washed away and has become slippery for Buses. Aggregate blocking drains | (PEL Email to FRA 17/12/16 at 4:55pm) | Restricted/Delayed Bus Services | Inspect & program repairs once TD04F finishes | TBC |   | Pending |
| Natua | Vunivau/Bua Circular Road | On Hill past Maya Ram Shop | Aggregate washed away and has become slippery for Buses. | (PEL Email to FRA 17/12/16 at 4:55pm) | Restricted/Delayed Bus Services | Inspect & program repairs once TD04F finishes | TBC |   | Pending |
| Natua | Labasa/Dama/Nabouwalu u/Solevu/Nasolo/Dama/Kiobo | The road past Nasolo village; there is a hill called Nababa. Past the Nasawana cement hill. | Aggregate washed away and has become slippery for Buses. | (PEL Email to FRA 17/12/16 at 4:55pm) | Open to all traffic | Inspect & program repairs once TD04F finishes | TBC |   | Completed |
| Savusavu | Kubulau Peninsular Rd | Small section on road with slippery and boggy surface.  | Aggregate washed away and has become slippery for Buses. Further additional programmed maintenance work includes positive drainage maintenance and additional metalling, grading and compaction |  (Email FHH to FRA 17/12/16) | Open to all traffic | Place aggregate followed by Positive drainage maintenance once TD04F finishes |   | 8:00am 22/12/16 | Completed |
| Natua | Nabaouwalu Road - Daria Hill | Solevu.Hill | Landslide | 7:00am 18/12/16 | Open to all traffic | Clear Landslide |   | 8:00am 19/12/16 | Completed |
| Taveuni | North Coastal Road | CH20000-23000 | Flooding through villages. Some areas of road underwater | 7:00am 18/12/16 | Open to all traffic |   |   | 8:00am 19/12/16 | Completed |
| Taveuni | South Coastal Road | 7km, 8km, 10-15km | Heavy rain continued from yesterday, scoured wheel tracks Hill sections | 7:00am 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 20/12/16 | Completed |
| Rabi | Rabi Coastal Road | CH300 | Road Drop Out - open to single lane only | 7:00am 18/12/16 | Open to all traffic - drive with care | Reinstate Drop out | TBC - Possibly by 27/01/17 |   | Pending |
| Rabi | Rabi Coastal Road | CH700 | Land slide fully blocked | 7:00am 18/12/16 | Closed to all Traffic | Clear Landslide | TBC - Possibly by 27/01/17 |   | Pending |
| Rabi | Rabi Coastal Road | Between Nuku to Buokanikai  | Slips and Land Slide  | 7:00am 18/12/16 | Closed to all Traffic | Clear Landslide | TBC - Possibly by 27/01/17 |   | Pending |
| Savusavu | Transinsular Road | CH42000. Between FHH Yard at Savusavu Town | Fallen Tree blocking entire road | 7:00am 18/12/16 | Open to all traffic | Remove tree | 9:00am 18/12/16 | 8:00am 18/12/16 | Completed |
| Labasa | Wainikoro Road | CH12000 | Underwater | 8:00am 18/12/16 | Open to all traffic | Wait for water to recede | 12:00pm 18/12/16 | 12:00pm 18/12/16 | Completed |
| Labasa | Siberia Road | CH4000 - underwater from Emily Point towards Vunicuicui. | Underwater | 8:00am 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Bulileka Road | Qawa, Dreketilailai Bridge | Underwater | 8:00am 18/12/16 | Open to all traffic | Wait for water to recede | TBC | 8:00am 19/12/16 | Completed |
| Labasa | Nakama Crossing | Nakama Crossing | Underwater | 8:00am 18/12/16 | Open to all traffic | Wait for water to recede | TBC | 8:00am 19/12/16 | Completed |
| Labasa | Naduna Road | Naduna Road | Underwater | 8:00am 18/12/16 | Open to all traffic | Wait for water to recede | 12:00pm 18/12/16 | 12:00pm 18/12/16 | Completed |
| Labasa | Urata Crossing | Urata Crossing | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00pm 19/12/16 | Completed |
| Savusavu | Viani Road | 1.5km | Cuvlert cover down stream end washout. | 12:00pm 18/12/16 | Open to all traffic | Awaiting water to recede - backfill washout | 5:00pm 28/12/16 |   | Completed |
| Savusavu | Viani Road | 4.5km | Landslide | 12:00pm 18/12/16 | Open to all traffic | Clear Landslide | 3:00pm 18/12/16 | 3:00pm 18/12/16 | Completed |
| Savusavu | Natewa West Cosat Rad | 5km | Landslide | 12:00pm 18/12/16 | Open to all traffic | Clear Landslide |   | 8:00am 20/12/16 | Completed |
| Savusavu | Natewa West Cosat Rad | Tabia Flat - 16km | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede | 3:00pm 18/12/16 | 3:00pm 18/12/16 | Completed |
| Savusavu | Nabua Rd | First 300m | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede | 3:00pm 18/12/16 | 3:00pm 18/12/16 | Completed |
| Savusavu | Bucabay | Navava - 26km | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede | 3:00pm 18/12/16 | 3:00pm 18/12/16 | Completed |
| Savusavu | Bucabay | Salt Lake 31km | Flooding Debris and silt, very slippery | 12:00pm 18/12/16 | Open to all traffic | Sweep loose material. Crew On site at 12:00pm 18/12/16 | 3:00pm 18/12/16 | 3:00pm 18/12/16 | Completed |
| Savusavu | Nakobo  | Mataikoro 6km | Landslide | 12:00pm 18/12/16 | Open to all traffic | Clear Landslide | 6:00pm 20/12/16 | 8:00am 21/12/16 | Completed |
| Savusavu | Kubulau Peninsular Rd | Kilaka 27km |  Approach washout - downstream end | 12:00pm 18/12/16 | Open to all traffic | Backfilling Washout | 6:00pm 18/12/16 | 6:00pm 18/12/16 | Completed |
| Taveuni | North Coastal Road | Welagi 15km | Fallen Rock | 12:00pm 18/12/16 | Open to all traffic | Clear fallen rock | 2:00pm 18/12/16 | 2:00pm 18/12/16 | Completed |
| Labasa | Bocalevu Road | Bocalevu Road | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Tabicola Road | Near railway Line | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Delaikoro Road | Delaikoro Road at multiple locations | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Korotari Road | Between Corner Shop to sector office | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Vunimoli Crossing | Vunimoli Crossing | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Labasa | Wainikoro Road | CH17000 - 20000 | Underwater | 12:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Savusavu | Bucabay | Navonu-Loa 60km | Landslide | 2:00pm 18/12/16 | Open to all traffic | Clear Landslide | 6:00pm 18/12/16 | 6:00pm 18/12/16 | Completed |
| Savusavu | Dakuniba-Natuvu | 3km | Fallen Coconut Trees | 2:00pm 18/12/16 | Open to all traffic | Clear fallen trees | 6:00pm 18/12/16 | 6:00pm 18/12/16 | Completed |
| Natua | Nabouwalu Road | near Qaloyaga Bridge | Underwater | 4:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Natua | Qaloyaga Road | Qaloyaga Road | Underwater | 4:00pm 18/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 19/12/16 | Completed |
| Savusavu | Kubulau Peninsular Rd | Raviravi 16km | Road Drop Out - open to single lane only | 5:00pm 18/12/16 | Single lane open, drive with care | Phase1 Repairs Completed. | Phase 2 restoration in progress |   | Pending |
| Natua | Nabouwalu-Daria | Wainikorodamu Bridge | Approach Washout | 6:00pm 18/12/16 | Open to all traffic | Reinstate Washout  |   | 4:00pm 22/12/16 | Completed |
| Natua | Zailav | Zailav | Underwater | 7:00am 18/12/16 | Open to all traffic | Wait for water to recede. Water gas receded. Debris to be cleared | TBC |   | Completed |
| Natua | Nabouwalu Daria | Navave | Landslide | 3:00pm 18/12/16 | Open to all traffic | Clear Landslide |   | 8:00am 19/12/16 | Completed |
| Natua | waikonadawa in Namouwalu crossing | waikonadawa in Namouwalu crossing | Underwater | 12:00pm 19/12/16 | Open to all traffic | Wait for water to recede.  |   | 4:00pm 22/12/16 | Completed |
| Natua | waikonadawa in Namouwalu crossing | Waikonadawa in Namouwalu crossing | Small Slips along road | 12:00pm 19/12/16 | Open to all traffic | Clear Slips  | TBC |   | Completed |
| Natua | Nabouwalu Road | Road Blocked at Vuya | FRA was informed this Morning by PA Bua that the subjected portion of the this road is blocked. | 12:00pm 19/12/16 | Open to all traffic | Clear slips and repair road drop out |   | 12:00pm 122/12/16 | Completed |
| Natua | Nabouwalu Daria | Delaidrove  | Landslide | 12:00pm 19/12/16 | Open to all traffic | Clear Landslide | TBC |   | Completed |
| Natua | Nabouwalu Daria | Saolo bridge | Blocked by debris and if this is not attended to, water can spoil the approaches from either side.  | 12:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00pm 122/12/16 | Completed |
| Natua | Nabouwalu Daria | Nakawakawa bridge | Blocked by debris and if this is not attended to, water can spoil the approaches from either side.  | 12:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00pm 122/12/16 | Completed |
| Savusavu | Bagata | Bagata Bridge | Underwater | 12:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris. Water has receded |   | 4:00pm 21/12/16 | Completed |
| Savusavu | Wailevu West Coast  | Naviavia Bridge | Underwater | 12:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00PM 20/12/16 | Completed |
| Labasa | Urata Crossing | Urata Crossing | Bridge Approcahes scoured | 4:00pm 19/12/16 | Open to all traffic | Reinstate Bridge Approcahes. Rising waters may flood crossing again |   | 3:00pm 19/12/16 | Completed |
| Labasa | Qawa Crossing | Qawa Crossing | Crossing clear but Approaches underwater | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede |   | 4:00pm 20/12/16 | Completed |
| Natua | Vatudova Circular Road. | Movo Crossing | Culvert washed out. Pavement washed out. Loss of trafficable road width | 4:00pm 19/12/16 | Open to all traffic - drive with care | Reinstatement of culvert and pavement | 6;00pm 21/12/16 | 4:00pm 22/12/16 | Completed |
| Savusavu | Wailevu West Coast Rd | Valeni Bridge | Underwater | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00PM 20/12/16 | Completed |
| Savusavu | Wailevu West Coast Rd | Natua Bridge | Underwater | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00PM 20/12/16 | Completed |
| Taveuni | North Coastal Rd | North Coastal Rd - 31.7Km  | Landslide | 4:00pm 19/12/16 | Open to all traffic | Clear Debirs |   | 8:00am 20/12/16 | Completed |
| Taveuni | North Coastal Rd | North Coastal Rd - 35.1km | Landslide | 4:00pm 19/12/16 | Open to all traffic - drive with care | Clear Debirs |   | 12:00pm 21/12/16 | Completed |
| Taveuni | North Coastal Rd | North Coastal Rd - 35.8km | Landslide | 4:00pm 19/12/16 | Open to all traffic | Landslide removed | 6:00pm 19/12/16 | 4:00pm 21/12/16 | Completed |
| Labasa | Urata Crossing | Urata Crossing | Underwater - Photo taken at 3:40pm | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 4:00pm 20/12/16 | Completed |
| Labasa | Vuniyalayala Circular | 1924km | Gravel washout from culvert cover | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede then relay and backfill |   | 12:00pm 21/12/16 | Completed |
| Labasa | Vuniyalayala Circular | 2345km | Bridge approach to be reinstated. Gravel washout | 4:00pm 19/12/16 | Open to all traffic | Wait for water to recede then relay and backfill |   | 12:00pm 21/12/16 | Completed |
| Natua | Nabouwalu | Near Navave | Bogggy surface | 4:00pm 19/12/16 | Open to all traffic | Backfilling with boulders |   | 4:00pm 20/12/16 | Completed |
| Natua | Nabouwalu | Nasolo hill | Road sink | 4:00pm 19/12/16 | Open to all traffic | Backfilii | 6.00am 20/12/16 | 12:00pm 22/12/16 | Completed |
| Labasa | Siberia Road | At Emily Point | Underwater | 4:07pm 19/12/16 | Open to all traffic | Wait for water to recede. |   | 4:00pm 20/12/16 | Completed |
| Labasa | Siberia Road | Culvert 2/1 | Underwater - Blocked Culvert 2/1 | 4:07pm 19/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 4:00pm 20/12/16 | Completed |
| Labasa | Covata Korowiri Road | Culvert Crossing | Underwater | 6:26pm 19/12/16 | Open to all traffic | Wait for water to recede. Water receded |   | 8:28am 20/12/16 | Completed |
| Labasa | Wainikoro | Before Nubu Village | Road Drop Out  | 4pm 19/12/16 | Open to all traffic | Backfill  |   | 4:00pm 20/12/16 | Completed |
| Labasa | Bulileka Road | Dreketilailai Crossing | Underwater  | 7am 20/112/16 | Open to all traffic | Wait for water to recede then relay and backfill approaches |   | 4:00pm 20/12/16 | Completed |
| Labasa | Wainikoro | Soasoa Flats | Underwater | 7am 20/12/16 | Open to all traffic | Wait for water to recede. Water Receded |   | 12:00pm 20/12/16 | Completed |
| Labasa | Nakelikoso Road | Before and after Nakelikoso Crossing | Depressions and boggy sections | 7am 20/12/16 | Open to all traffic | Crews moving to Nakelikoso to repair sections |   | 8:00am 21/12/16 | Completed |
| Natua | Naividamu | 1.5km | Road sink | 9:00pm 19/12/16 | Open to all traffic | Backfill with boulders |   | 4:00pm 20/12/16 | Completed |
| Natua | Koroinasolo | 1.2km | Crossing scour/flooding | 3.00pm 19/12/16 | Open to all traffic | Wait for water to recede | TBC |   | Completed |
| Savusavu | Nasinu Rd | 600m | Road Dropout | 9:00am 20/12/16 | Open to all traffic | Reinstate road dropout |   | 8:00am 21/12/16 | Completed |
| Savusavu | Natewa West Cosat Rad | 53km - Pass Navetau | Culvert washout | 9:00am 20/12/16 | Open to all traffic | Replace Broken Culvert | 5:00pm 29/12/16 |   | Phase 1 complete/work in progress |
| Savusavu | Natewa West Cosat Rad | 53.3km - Pass Navetau Village | Culvert Cover Wasout | 9:00am 20/12/16 | Open to all traffic | Backfill washout | TBC |   | Completed |
| Savusavu | Napuka Rd | 11.8km - Before Kanakana Village | Culvert washout | 9:00am 20/12/16 | Open to all traffic | Reinstate washout |   | 8:00am 21/12/16 | Completed |
| Savusavu | Napuka Rd | 30km Kubulau Estate | Culvert Wasout | 9:00am 20/12/16 | Open to all traffic | Reinstate washout |   | 8:00am 22/12/16 | Completed |
| Savusavu | Napuka Rd | 25Km | Road Edge Washout | 9:00am 20/12/16 | Open to all traffic - drive with care | Reinstate washout | 12:00pm 31/12/16 |   | Pending |
| Savusavu | Natewa Valavala Rd | 24.8km Wailevu | Bridge Approach Washout | 9:00am 20/12/16 | Open to all traffic - drive with care | Reinstate washout | 12:00pm 31/12/16 |   | Pending |
| Taveuni | North Coastal Rd | Bouma Bridge | Bridge Approach Washout | 9:00am 20/12/16 | Open to all traffic | Reinstate washout |   | 8:00am 21/12/16 | Completed |
| Taveuni | North Coastal Rd | 38km to 42km Road End | Land Slide - 10 sites | 9:00am 20/12/16 | Open to all traffic | Clear Land Slide | TBC |   | Pending |
| Savusavu | Natewa West Cosat Rad | 37km Nacolase | Fallen Tree blocking road access | 9:00am 20/12/16 | Open to all traffic | Remove fallen tree |   | 8:00am 21/12/16 | Completed |
| Savusavu | Natewa West Cosat Rad | 16km Tabia Flat | Underwater | 4:00pm 20/12/16 | Open to all traffic | Wait for water to recede |   | 8:00am 21/12/16 | Completed |
| Natua | Nabouwalu Road | After 30Km marker | 9x Landslides | 4:00pm 20/12/16 | Open to all traffic | Clearing Land slides. Working from one landslide to the next |   | 8:00am 21/12/16 | Completed |
| Natua | Nabouwalu Road | After 30Km marker | 2x Crossing washouts | 4:00pm 20/12/16 | Open to all traffic | Reinstate  |   | 12:00pm 22/12/16 | Completed |
| Natua | Nabouwalu Road | After 30Km marker | 4 x road sinks drop outs & erosion | 4:00pm 20/12/16 | Open to all traffic | Reinstate  |   | 12:00pm 22/12/16 | Completed |
| Labasa | Delaikoro Road | Taganiwaqa Crossing | Approach Washout | 2:45pm 20/12/16 | Open to all traffic | Wait for watet to recede then reinstate approaches |   | 12:00pm 22/12/16 | Completed |
| Labasa | Delaikoro Road | Nasaqa Crossing | Approach Washout | 2:45pm 20/12/16 | Open to all traffic | Wait for water to recede then reinstate approaches |   | 12:00pm 22/12/16 | Completed |
| Labasa | Nakoro Street | Nakoro Street | Metal washed away | 4:30pm 20/12/16 | Open to all traffic | Reinstate Metal aggregate and compact | 5:00pm 28/12/16 |   | Completed |
| Natua | Past Naduri village towards Kadavu. | Past Naduri village towards Kadavu. | Culvert washed away and damaged | 7:26pm 20/12/16 | Open to all traffic | Reinstate Culvert | TBC |   | Completed |
| Natua | Past Naduri village towards Kadavu. | Past Naduri village towards Kadavu. | Crossing approaches scoured out | 7:26pm 20/12/16 | Open to all traffic | Reinstate aggregate at crossing apporoaches and clear debris | TBC |   | Completed |
| Natua | Past Naduri village towards Kadavu. | Past Naduri village towards Kadavu. | Scoured Crossing approaches and wingwalls | 7:26pm 20/12/16 | Open to all traffic | Reinstate Crossing Approaches | TBC |   | Completed |
| Natua | Cavaga Road | Solevu, Bua | Damaged road pavement - large crack in road | 10:07pm 20/12/16 | Open to all traffic | Repair Pavement surface and remetal | TBC |   | Completed |
| Natua | Nakorolevu Bridge | Sawani, Nadi, Bua | Underwater | 10:07pm 20/12/16 | Open to all traffic | Wait for water to recede. Clear Debris |   | 12:00pm 22/12/16 | Completed |
| Natua | Natewa Settlement Road | Vuya, Bua | Boggy Pavement surface | 10:07pm 20/12/16 | Open to all traffic | Repair Pavement surface and remetal |   | 12:00pm 22/12/16 | Completed |
| Natua | Naividamu | 10.6km | Bogggy surface | 5.20pm 20/12/16 | Open to all traffic | Back filling & metalling | 22.12.2016 | 12:00pm 22/12/16 | Completed |
| Natua | Naseva A | 154 | Culvert washout | 9am 21/12/2016 | Open to all traffic | Reinstate open trench/backfill | 7:00pm 21/12/16 | 12:00pm 22/12/16 | Completed |
| Natua | Nabouciwa | 1.249 | Road scour/flooded road | 9.00am 21/12/16 | Open to all traffic | Drainage + Metalling | 5:00pm 29/12/16 |   | Completed |
| Natua | Navidamu | 4.793 - 7.553 | Slippery condtions + boggy surface + potholes | 10.30am 21/12/16 | Open to all traffic | Metalling | 8:00am 22/12/16 |   | Completed |
| Labasa | Nasekula Village Road | 1st culvert from Nabouwalu Rd end | Culvert Cover Wasout | 9:00am 21/12/2016  | Open to all traffic | Backfill material to existing road level |   | 4:00pm 21/12/16 | Completed |
| Labasa | Delaikoro Road | Kawakawa Cemetary | Depressed boggy sectiions | 10:46am 21/125/16 | Open to all traffic | Grade of soft material and metal/compact |   | 4:00pm 21/12/16 | Completed |
| Labasa | Savusavuitaqa Rd |   | Collapsed culvert | 10:46am 21/12/16 | Open to all traffic | Excavate relay culvert and backfill. NOTE FALSE ALARM NO CULVERT |   | 4:00pm 21/12/16 | Completed |
| Labasa | Namoli Rd | Past Namoli Village | Scouring at inlet end | 10:55am 21/12/16 | Open to all traffic | Excavate relay culvert and backfill | TBC |   | Completed |
| Labasa | Naduna Road | Nakama Crossing | Underwater | 11:00am 21/12/16 | Open to all traffic | Wait for water to recede |   | 4:00pm 21/12/16 | Completed |
| Savusavu | Natewa West Cosat Rad | Nabua Flat | Saturated Pavement | 2:00pm 21/12/16 | Open to all traffic | Pavement Repairs, drainage work | 5:00pm 21/12/16 | 4:00pm 22/12/16 | Completed |
| Savusavu | Dawara Rd | CH150 | Landslide | 2:00pm 21/12/16 | Open to all traffic | Remove Landslide materiial |   | 8:00am 22/12/16 | Completed |
| Savusavu | Dakuniba | Nawi Hill | Slippery condtions  | 2:00pm 21/12/16 | Open to all traffic | Caution drivers. Remetal as required | 6:00pm 24/12/16 |   | Completed |
| Savusavu | Dakuniba Rd | Nawi to Dakuniba | 3 Landslide, 1 Road Dropout | 2:00pm 21/12/16 | Open to 4x4 only, drive with care | Remove lanslide and repair drop outs | 5:00pm 31/12/16 |   | Phase 1 complete/work in progress |
| Labasa | Naduna Road | Nakama Crossing | Underwater | 3:06pm 21/12/16 | Open to all traffic | Water has receded. Debris from bridge deck has been cleared. Debris on upstream end still needs to be cleared. Open to traffic. | 2:00pm 22/12/16 | 4:00pm 22/12/16 | Completed |
| Labasa | Vunivau Circular | Past Valebasoga JNC | Blocked culvert inlet | 6:00pm 21/12/16 | Open to all traffic | Remove debris blockage | 5:00pm 23/12/16 |   | Completed |
| Labasa | Wainikoro Rd | Culvert 13/2 | Blocked culvert inlet | 7:00pm 21/12/16 | Open to all traffic | Remove debris blockage | 5:00pm 23/12/16 |   | Completed |
| Labasa | Nayarabale Road | Culvert 0/1 | Culvert washed out. Pavement washed out. Loss of trafficable road width | 11:30am 22/12/16 | Open to all traffic | Reinstate Pavement with AP65 Material and compact | 5:00pm 23/12/16 |   | Completed |
| Labasa | Nakorotari Road | Navakuru Crossing | Washout of approaches and debris upstream end | 11:30am 22/12/16 | Open to all traffic | Wait for water to recede. Reinsattement of crossing approaches and removal of upstream debris | 5:00pm 23/12/16 |   | Completed |
| Labasa | Qeleimumu Rd | Qeleimumu Crossing | Washout of approaches and debris upstream end | 2:03pm 22/12/16 | Open to all traffic | Wait for water to recede. Reinstatement of crossing approaches and removal of debris. Bus services and RSL still servicing since it’s a circular road. |  12:00pm 31/12/2016 |   | Completed |
| Savusavu | Natewa West Cosat Rad | 6km  | Road Dropout | 6:00pm 22/12/16 | Open to all traffic - drive with care | Reinstate road dropout - Work in Progress | 5:00pm 31/12/16 |   | Phase 1 complete/work in progress |
| Labasa | Vunivutu Rd | Culver 1/5 | Gravel washout from culvert cover | 9:00am 23/12/16 | Open to all traffic - drive with care | Backfill with AP40 | 5:00pm 24/12/16 |   | Completed |
| Labasa | Vunivutu Rd | Culvert 4/1 | Collapsed culvert | 9:00am 23/12/16 | Open to all traffic - drive with care | Excavate and Relay | 5:00pm 24/12/16 |   | Completed |

**EASTERN DIVISION**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Depot | Road Name | Location Description | Status of Damage | Time/Date Reported | Advice to Motorists | FRA Contractors Action that Will be Taken | Expected Road Opening Date | Time/Date Resolved | How Resolved |
| KORO | KORO CIRCULAR Road  | Kade to Navaga | Land Slide and Fallen trees  | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| KORO | Koro Circular Road | Nauru culvert | Bridge approach washout | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| KORO | Koro Circular Road | Tuatua Bridge Nasau Bridge Nakodu to loma flat | All low line crossing FLOODING | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| GAU | Gau Circular Road | Landslide Nukuloa-Lovu | Landslide | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| GAU | Gau Circular Road | Nabulibo Bridge ch -55km | Both bridge approach Washout | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| Gau  | Jetty Road | Nawaikama | Landslide | 21/12/16 3pm | open |   |   | 20.12.19 |   |
| Gau | Gau Circular | Navukailagi to Qarani | Landslide | 21/12/16 3pm | close | Depot Jcb will work on the slide from 22/12/16 |   | Mid-January |   |
| Vanuabalavu | Mualevu Road |   | Landslide one side | 21/12/16 3pm | open |   |   | 19.12.16 |   |
|
| Vanuabalavu | Mualevu Road | Culvert head  | Culvert headwall one side washout | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| Vanuabalavu | Mualevu Road | Vatu Culvert  | Culvert scoring and washout | 21/12/16 3pm | open |   |   | 19.12.16 |   |
| Vanuabalavu | Boitaci Road |   | Landslide | 21/12/16 3pm | Half road open |   | 23.12.16 |   |   |
|  Moala | Ketera Road | Muanaivoco | Landslide | 21/12/16 3pm | Open |   |   | 20.12.16 |   |
| Moala | Ketera Road | Nukuleka + 2 | 2 Landslide | 21/12/16 3pm | Open |   |   | 20.12.16 |   |