## Summary
Procurment Tender Summary
Planning Stages | RFT's In Process | Advertised | Evaluation Stages | Total
5 | 4 | 16 | 12 | 37

## Status
FRA Procurement Tender Status
No | Type of Work | Contract Number | Name of Work | Division | Date of Advertisement | Closing Date | Advertised/RFT's In Process/Evaluation Stage/ Planning Stage | EOI/RFT/RFP
1 | Rural Roads | FRA 17/43 | Nasauvakarua Stage 2 | Western | 2017-06-21 | 2017-08-17 | Evaluation Stages | RFT
2 |  | FRA 17/45 | Draubuta Access Road | Western | 2017-06-21 | 2017-08-17 | Evaluation Stages | RFT
3 |  | FRA 17/46 | Matokana Stage 2 | Western | 2017-06-21 | 2017-08-17 | Evaluation Stages | RFT
4 |  | FRA 17/61 | Lagi - Duavata | Central | 2017-07-26 | 2017-09-12 | Advertised | RFT
5 |  | FRA 17/62 | Dreketilailai - Lekutulevu | Central | 2017-07-26 | 2017-09-12 | Advertised | RFT
6 |  | FRA 17/60 | Nakorosule - Nawaisomo | Central | 2017-07-26 | 2017-09-12 | Advertised | RFT
7 |  | FRA 17/59 | Namata Village Access | Central | 2017-07-26 | 2017-09-12 | Advertised | RFT
8 |  | FRA 17/66 | Kiuva - Kaba Peninsula Road | Central | 2017-07-28 | 2017-09-12 | Advertised | RFT
9 |  | FRA 17/58 | Natila Access Road | Central | 2017-07-26 | 2017-09-12 | Advertised | RFT
10 |  |  | Sawanikula - Korovou - Nasauvere | Central |  |  | Planning Stages
11 |  |  | Kadavu - Niurua - Raviravi | Northen |  |  | Planning Stages
12 | Crossings & Bridges | FRA 17/50 | Savusavu Crossing | Western | 2017-06-27 | 2017-08-03 | To be awarded | RFT
13 |  | FRA 17/52 | Burelevu Crossing | Western | 2017-06-27 | 2017-08-03 | To be awarded | RFT
14 |  | FRA 17/51 | Sawene Crossing | Western | 2017-06-27 | 2017-08-03 | Project on hold | RFT
15 |  | FRA 17/63 | Vakabuli - Paipai No.2 Crossing | Western | 2017-07-28 | 2017-09-14 | Advertised | RFT
16 |  | FRA 17/65 | Emuri Crossing | Western | 2017-07-28 | 2017-09-14 | Advertised | RFT
17 |  | FRA 17/64 | Nausori Crossing | Western | 2017-07-28 | 2017-09-14 | Advertised | RFT
18 |  |  | Waibula Crossing | Northen |  |  | Planning Stages
19 |  |  | Vunikawakawa Crossing | Northen |  |  | Planning Stages
20 |  |  | Balenabelo Crossing | Northen |  |  | Planning Stages
21 | Streetlights | FRA 17/47 | Queens Road | Western | 2017-06-19 | 2017-08-10 | Evaluation Stages | RFT
22 |  | FRA 17/48 | Kings Road | Central | 2017-06-19 | 2017-08-10 | Evaluation Stages | RFT
23 |  | FRA 17/54 | Navua Road | Western | 2017-03-07 | 2017-08-10 | Evaluation Stages | RFT
24 |  | FRA 17/69 | Labasa Road | Northen |  |  | RFT's In Process | RFT
25 | Business Operation | FRA17/49 | ERP Project Management Consultant | Head Office | 2017-06-20 | 2017-07-20 | Evaluation Stages | RFT
26 |  | FRA 17/56 | Business Process Mapping Specialist | Head Office | 2017-07-03 | 2017-07-21 | Evaluation Stages | RFT
27 | Maintenance | FRA 17/35 | Western Area Road Maintenance Contract | Western |  |  | RFT's In Process | EOI
28 | Survey | FRA 17/67 | Engineering Survey Nabouwalu Road | Northen | 2017-07-28 | 2017-08-10 | Evaluation Stages | RFT
29 | Footpaths | FRA 17/68 | Footpath Renewal Western Division | Western | 2017-08-18 | 2017-09-14 | Advertised | RFT
30 |  | FRA 17/79 | Footpath Construction Central Division | Central |  |  | RFT's In Process | RFT
31 | Urban Roads | FRA 17/75 | Nausori Airport - Road Diversion - Phase 1 | Central | 2017-08-18 | 2017-09-14 | Advertised | RFT
32 |  | FRA 17/78 | Nausori Airport - Road Diversion - Phase 2 | Central |  |  | RFT's In Process | RFT
33 | Bus Shelters | FRA 17/76 | Construction of Urban Bus Shelters | All | 2017-08-18 | 2017-09-28 | Advertised | RFT
34 | Bridges | FRA 17/77 | Installation of Waidamu Bailey Bridge | Western |  |  | RFT's In Process | RFT
35 | Bridge Repair | FRA 16/85 | Concrete Bridge Deck Repair Replacements | Western | 2017-08-18 | 2017-09-28 | Advertised | RFT
36 | Unsealed Roads | FRA 17/70 | Unsealed Road Maintenance for Selected Roads in Western Division | Western | 2017-01-08 | 2017-08-22 | Evaluation Stages | EOI
37 |  | FRA 17/71 | Unsealed Road Maintenance for Selected Roads in Central Division | Central | 2017-01-08 | 2017-08-22 | Evaluation Stages | EOI
38 |  | FRA 17/72 | Unsealed Road Maintenance for Selected Roads in Northern Division | Northen | 2017-01-08 | 2017-08-22 | Evaluation Stages | EOI
39 | Slips | NA | Rakiraki Slip New Layout | Western | 2017-08-25 | 2017-09-01 | Advertised | RFP
40 | Road Humps | NA | Construction of Road Humps in Ba and Lautoka | Western | 2017-08-24 | 2017-09-05 | Shortlisted Contractors | RFP
41 | Drainage | NA | Pavement and Drainage Upgrade- Clopcott Street Driveway | Western | 2017-08-24 | 2017-09-01 | Shortlisted Contractors | RFP
| Bus Bay | FRA 17/80 | Contruction of New Bus Bay alongs kings Road in BA | Western | 2017-09-02 | 2017-09-18 | RFT's In Process | RFT
| Andhra Sangam Road Upgrade | FRA 17/81 | Sigatoka Andhra Sangam College Road and Korolevu Road Upgrade | Western | 2017-09-02 | 2017-09-18 | RFT's In Process | RFT
42 | Jetty Repair | NA | Savusavu Jetty Repair | Northen |  |  | Response under review for GHD and iTS Pacific, Calibre Consulting | RFP
43 | Environmental Services | NA | Vakabulipaipai Crossing Replacement | Western | 2017-08-25 | 2017-09-08 | Shortlisted Consultants | RFP
|  |  | EIA-Nausori Airport Road Diversion Route 1 | Central | 2017-09-01 | 2017-09-14 | Shortlisted Consultants | RFP